## Hoja1
Dimension | bullet_id | sub_id | indicator
1 | 1 | 0 | There is a documented, approved and binding RBM Policy within the government
1 | 1 | 1 | It is relevant across the government at all levels
1 | 1 | 2 | It outlines guiding principles / pillars that are alligned to a results-oriented approach
1 | 1 | 3 | It communicates what RBM entails (i.e., clear definitions for key concepts) and clearly states how it works
1 | 1 | 4 | It identifies key actors who are responsible for supervising and measuring the results and implementation of the RBM policy and their functions
1 | 1 | 5 | It identifies key actors who are responsible for the supervision and coordination of the RBM policy
1 | 1 | 6 | It is use-oriented in planning, budgeting and implementing towards results
1 | 1 | 7 | The funding for M&E activities and the responsibles are identified
1 | 2 | 0 | There are laws/regulations/norms* recognizing M&E activities across the government
1 | 2 | 1 | They are aditional to the RBM Policy
1 | 2 | 2 | They delegate M&E responsibilities to a single national body or to multiple MDAs
1 | 2 | 3 | It is relevant across the government at all levels and branches (i.e. scope of action) and defines the M&E subjects
1 | 2 | 4 | They stablish that the M&E results affect planning, budgeting and implementing activities
1 | 2 | 5 | (If more than one) They are consistent with each other
1 | 2 | 6 | It stablishes the need to designate focal points in each MDA across government
1 | 3 | 0 | There are guidelines that establish the rules and processes to perform monitoring activities
1 | 3 | 1 | They identify indicator types and the dimensions they want to measure (e.g., efficiency, efficacy), and monitoring tools (e.g., logic framework) to be developed for each project / social programme
1 | 3 | 2 | They identify specific timeframes to collect indicator data and develop monitoring tools to measure the indicators (e.g., collect every six months) for each project
1 | 3 | 3 | They have criteria to ensure data collection quality (design, measurement, report)
1 | 3 | 4 | They integrate the indicators as a monitoring system
1 | 3 | 5 | The monitoring system has a stablished process to update its information periodically
1 | 3 | 6 | The monitoring system has a stablished process to update its indicators periodically
1 | 3 | 7 | There are rules providing all parts in the monitoring process with a way of presenting their opinion (i.e. institutional positions)
1 | 4 | 0 | There are guidelines that establish the rules and processes to perform evaluation activities
1 | 4 | 1 | They identify key stakeholders to be part of the evaluation process (e.g. evaluation process coordinators, evaluation subjects, evaluation process implementators)
1 | 4 | 2 | They identify specific evaluation types
1 | 4 | 3 | The identify specific timeframes for each evaluation type
1 | 4 | 4 | They identify specific characteristics and functions of evaluators
1 | 4 | 5 | It establishes an iterative process of evaluation (i.e. is not a one-time exercise)
1 | 4 | 6 | They identify the elements to be included in the evaluation's ToRs (e.g. objectives of the evaluation, the role and responsibilities of the evaluator and evaluation client and the resources available to conduct the evaluation)
1 | 4 | 7 | They outline the operationalization process of the national evaluation agenda (i.e. it is agreed among relevant stakeholders)
1 | 4 | 8 | There have quality control mechanisms for evaluation activities (e.g. quality attribute listings, quality evaluations, peer review, satisfaction surveys, evaluate the evaluator)
1 | 4 | 9 | There are rules providing all parts in the evaluation process with a way of presenting their opinion (i.e. institutional position)
1 | 5 | 0 | There are guidelines that establish the rules and processes to address and use of M&E results
1 | 5 | 1 | They identify instruments to measure the RBM System results
1 | 5 | 2 | They identify mechanisms to use monitoring results
1 | 5 | 3 | They identify mechanisms to use evaluation results
1 | 5 | 4 | They establish rules and processes that require the budgeting process to consider the results of M&E activities (they make explicit the link between planning and budgeting)
1 | 6 | 0 | There are actions towards building an enabling environment
1 | 6 | 1 | There are strategies to enhance or attenuate possitive or negative incentives for the use of monitoring
1 | 6 | 2 | There are strategies to enhance or attenuate possitive or negative incentives for the use of evaluation
1 | 6 | 3 | There are mechanisms for the participation of stakeholders in the definition of monitoring activities and needs
1 | 6 | 4 | There are mechanisms for the participation of stakeholders in the definition of evaluation activities and needs
1 | 6 | 5 | There are periodic meetings involving relevant stakeholders to review the M&E information as an RBM System feedback exercise
1 | 7 | 0 | There is a Results Oriented National Plan defined for a given period in the country
1 | 7 | 1 | It has defined objectives
1 | 7 | 2 | It is constructed in a participatory process
1 | 7 | 3 | It is constructed using the information generated by the RBM System
1 | 7 | 4 | It has defined strategies to implement the plan
1 | 7 | 5 | It is evaluated by mandate
1 | 7 | 6 | It has specific evaluation activities
1 | 7 | 7 | It has defined responsible actors
1 | 7 | 8 | It considers regional (CARICOM) objectives
1 | 8 | 0 | There is a national budgeting strategy for a given period in the country
1 | 8 | 1 | It is allocated according to the objectives/goals/activities of the national planning
1 | 8 | 2 | It is allocated using the information generated by evnidence and the RBM System
1 | 8 | 3 | Its allocation is updated according to the evidence derived from the M&E activities
1 | 8 | 4 | The budget allocation is defined in annual terms (i.e. it specify the starting date, relevant milestones dates, and the end date)
1 | 8 | 5 | It stabishes a specific allocation of resources for M&E activities according to the budget period
1 | 8 | 6 | It considers the prioritization of the objectives/goals/activities identified in the national planning
1 | 8 | 7 | It is constructed using the information generated by the RBM System
1 | 8 | 8 | It considers other available information to define its allocation (e.g national statistics/poverty measurements/etc.)
2 | 9 | 0 | There are operative handbooks to implement the monitoring functions (i.e. Logic Framework)
2 | 9 | 1 | They identify all the relevant activities to develop each stage of the process (e.g.specific activities within the analysis of the project's context, stakeholder)
2 | 9 | 2 | They outline specific timeframes to implement every stage of the process
2 | 9 | 3 | They identify the responsibles in every stage of the process (specific MDAs and units within the MDAs)
2 | 9 | 4 | They outline a dissemination strategy of the LF results (what, how, when and to who do you want to diffuse the results)
2 | 10 | 0 | There are operative handbooks that establish specific steps to develop each stage of the evaluation function
2 | 10 | 1 | They identify all the relevant activities to develop each stage of the evaluation process (e.g. evaluators selection, ToR definition for each evaluation, evaluation supervision)
2 | 10 | 2 | They outline specific timeframes to implement every stage of the process
2 | 10 | 3 | They outline a dissemination strategy of the evaluation results (what, how, when and to who do you want to diffuse the results)
2 | 10 | 4 | They identify the responsible (specific MDAs and units within the MDAs) in every stage of the process
2 | 11 | 0 | 11. There is an operating and functioning M&E system at the national or/and subnational levels
2 | 11 | 1 | It is homogeneous across the government and holds a common language in concepts of M&E
2 | 11 | 2 | It is integrated at various levels of government (national and subnational)
2 | 11 | 3 | It is known by all sectors and MDAs* in government
2 | 11 | 4 | It is relevant (e.g. it recollects indicator data that is necessary, pertinent, and timely, it involves key stakeholders at different levels)*
2 | 11 | 5 | It generates timely documents for specific evidence users*
2 | 11 | 6 | It generates use-oriented documents for specific evidence users*
2 | 11 | 7 | It is sufficiently funded (specific financial resources are allocated)
2 | 12 | 0 | There is a defined human resources structure for M&E activities
2 | 12 | 1 | It has specific focal points in each MDA across the government
2 | 12 | 2 | The MDA focal points constitute a coordinated network that is part of the M&E System
2 | 12 | 3 | The MDA focal points have clear functions, responsibilities and expected outcomes
2 | 12 | 4 | The MDAs focal points become recognized strategic areas of information about the performance and impact of the MDAs projects / programmes.
3 | 13 | 0 | There are sufficient private and public entities providing M&E services, including training, to the public sector.
3 | 13 | 1 | They provide a variety of M&E services (e.g conduct diagnostics, evaluations, assessments)
3 | 13 | 2 | They provide a broad academic offer for RBM capacity building (e.g continous courses / diplomas in M&E topics, specific training to the public sector )
3 | 14 | 0 | There are skilled personnel in government with technical capacity and competencies to conduct planning and budgeting for results
3 | 14 | 1 | They have technical skills to use derived evidence from M&E (identify priorities, vulnerable population, what works to attend that priorities)
3 | 14 | 2 | They have competencies to coordinate with other MDAs and relevant actors
3 | 14 | 3 | They have competences to use M&E results to define results-oriented budgeting ( e.g., identify priorities, new public problems that should be adressed, policies that work, compare between policies)
3 | 14 | 4 | They have soft skills (negotiation skills) **
3 | 15 | 0 | There are skilled personnel in government with technical capacity and competencies to conduct monitoring activities
3 | 15 | 1 | They have technical skills to collect indicator data
3 | 15 | 2 | They have technical skills to use monitoring tools
3 | 15 | 3 | They have the competences to identify monitoring needs in order to collect relevant, pertinent and timely data
3 | 16 | 0 | There are skilled personnel in government with technical capacity and competencies to conduct evaluations and evaluation activities
3 | 16 | 1 | They have the competences to perform different evaluation types (e.g. design, process, impact) and use different methodologies (i.e., quantitative, qualitative, mixed-methods)
3 | 16 | 2 | They have the competences to identify evaluation needs and match them with proper evaluation types and methodologies: define evaluation horizon and ask relevant evaluation questions
3 | 16 | 3 | They have the competences to formulate reports that include relevant, pertinent and timely information for different stakeholders
3 | 16 | 4 | There is a capacity strengthening plan for on-going training in RBM and M&E
4 | 17 | 0 | RBM documents are publicly available for consultation
4 | 17 | 1 | National planning documents are publicly available
4 | 17 | 2 | National budget plans are publicly available
4 | 17 | 3 | Documents that mention the results/findings/recommendations of monitoring and evaluation activities are publicly available
4 | 17 | 4 | M&E manuals / guidelines /ToRs are publicly available
4 | 17 | 5 | There are mechanisms for the institution to know how much its reports and publications on M&E are downloaded or used by citizens
4 | 17 | 6 | There are mechanisms for the institution to know how much its reports and publications on M&E are downloaded or used by citizens
4 | 18 | 0 | There is an enabling environment for the use of M&E results
4 | 18 | 1 | There are explicit possitive or negative incentives for the use of monitoring results
4 | 18 | 2 | There are explicit possitive or negative incentives for the use of evaluation results
4 | 19 | 0 | M&E results are systematically included in the planning of government programs, policies, and projects (interventions)
4 | 19 | 1 | They are used in an institutionalized way: they follow a established procedure
4 | 19 | 2 | There are action plans or other management instruments to ensure M&E results/recommendations are implemented
4 | 19 | 3 | They justify the creation and design of government interventions
4 | 19 | 4 | They identify the target population of government interventions
4 | 19 | 5 | They identify general and specific recommendations to improve the implementation of government interventions
4 | 19 | 6 | They inform the design/redesign of government interventions
4 | 19 | 7 | They inform the initial budget allocations of government interventions
4 | 19 | 8 | They inform the budget increase/decrease/suspension of government interventions
4 | 19 | 9 | Evaluation findings/reports are updated periodically
4 | 19 | 10 | The M&E results are used to define the MDAs budget